## Slide 1: WP7 Project Management
H2020 LEIT RIA - ICT-10-2016 – Software Technology
2016/12/01 – 2019/11/30
Caroline Landry
Project Technical Manager
INRIA, France

## Slide 2: Tracking (1)
Meetings
  Monthly calls with all partners
  WP5 & WP4: regulars calls with all partners
  WP1, WP2 and WP3: dedicated calls and working sessions by video conferences
  KTH/INRIA: weekly calls
  9 in-person meetings

## Slide 3
Tracking (2)
Deliverables
Milestones
Actions

## Slide 4
Risks management
Tracking (3)

## Slide 5: Tracking (4)
Unplanned activities (PR2)
  Amendment
    Change tasks assignments of T1.4 and 5.4 from ATOS Turkey to ATOS IT
    Update WP3 objectives, task 3.2, deliverables D3.2 and D3.3 deadline
    Update WP4 task 4.1
    Update WP5 project KPIs
    Updated version of the DoA part A
    Updated version of the DoA part B
    Request letter
  Document reviews
    Revised version of D1.2
    Revised version of D3.1
    Revised version of D3.2
  Additional project interim review

## Slide 6: Deliverables

## Slide 7: Milestones

## Slide 8: Advisory board
Workshops
  December 2017, Madrid
  October 2018, Paris
  January 2019, Sophia
Members
  Henry Coles (PIT),
  Francisco Gortazar (University Rey Juan Carlos)
  Manuel Martinez (Nokia)

## Slide 9: Project KPIs

## Slide 10: Effort (1)
Chart: Effort M1-M36 per work package
| wp1 | wp2 | wp3 | wp4 | wp5 | wp6 | wp7
planned m1-m36 | 87 | 82 | 65 | 84 | 117 | 63 | 18
actual m1-m36 | 91.61 | 101.25 | 61.25 | 83.9 | 138.34 | 71.6 | 21.29

## Slide 11: Effort (2)
Chart: Effort M1-M36 per partner
| KTH | INRIA | SINTEF | TUDelft | OW2 | XWiki | ATOS | Aeon | ENG | TellU
planned | 9 | 79 | 50 | 56 | 53 | 61 | 63 | 56 | 59 | 30
actual | 25 | 83 | 60 | 66 | 54 | 61 | 63 | 61 | 59 | 37

## Slide 12: Effort (3)

## Slide 13: Effort (4)
KTH
  planned efforts were underestimated when moving
INRIA
  Some PMs moved from WP3 to WP1
  Some additional PMs allocated to WP1 to achieve the industrial maturity level
  Unplanned tasks (additional review, amendments and detailed management of some partners)
SINTEF
  Mainly additional effort on WP2 because of turnover

## Slide 14: Effort (5)
TUDelft
  Effort was divided differently mainly because of WP3 reorientation after mid-term review
OW2
  Difficulty to hire people impacted WP1/WP2
  PMs re-allocated to WP5 to implement CI tools
  More dissemination than planned and additional effort on exploitation and business plan to help Activeeon (WP6)
XWiki
  Technical work in WP1/WP2 faster than planned
  Effort re-allocated mainly on WP5 to achieve the metrics and the KPIs

## Slide 15: Effort (6)
Tellu
  WP3 contribution faster than planned and so some effort shifted from WP3 to WP2
  Additional effort on WP5 in the final year to work on TelluCloud
Activeeon
  2PMs achieved by INRIA on WP1 because of turnover (PR1)
  More effort on WP2/WP3/WP4/WP5 because of 1 senior engineer replaced by 2 junior engineers

## Slide 16
Personnel costs
Chart: Personnel costs per partner
| KTH | INRIA | SINTEF | TUDelft | OW2 | XWiki | ATOS | Aeon | ENG | TellU
budget | 66229 | 351711 | 511200 | 452984 | 291712 | 228300 | 283500 | 316000 | 295000 | 282274
actuals | 80360.57 | 400658 | 480341.13 | 467682.96 | 310504 | 269789.72 | 327628.84 | 298857.73 | 305193.81 | 341570

## Slide 17
Questions & Answers
17